SAEM 2026 AI Consensus Conference

Artificial Intelligence and Emergency Medicine: Technology, Training, Self, and Society

Project Plan: Path to Completion

May 21, 2026  |  Atlanta Marriott Marquis  |  SAEM Annual Meeting

Last updated: April 1, 2026

Andrew Taylor, MD MHS  |  University of Virginia

# 1. Current Status and Honest Assessment

Today is April 1, 2026. The conference is May 21. That gives us 7 weeks and 2 days.

What we have:

- Five well-defined working groups with descriptions mapped to the conference subtitle

- Ten co-leads identified across all five groups (see Section 2)

- A detailed leader guide with process, timeline, Delphi methodology, and deliverables

- Personalized invitation emails drafted and ready to send

- A planning committee of five UVA faculty plus administrative support

- SAEM institutional support and commitment to publish proceedings

- Conference plan document (originally written for AHRQ, adaptable to current scope)

What we don’t have yet:

- Confirmed co-leads — emails have not been sent. This is the single most critical bottleneck.

- Working group members — recruitment cannot start until co-leads accept

- A finalized conference agenda for the 1-room, $20-30K budget reality

- Keynote speaker or panelists

- Evidence briefs for each working group

- Budget approval or registration setup

- Any Delphi process work

The original leader guide assumed a March 16 start with kickoff meetings on March 30. We are now two weeks behind that timeline. The plan below resets all dates to an April 1 start and compresses accordingly. It is tight but achievable if co-lead confirmations come in by April 4 and recruitment moves fast.

# 2. Working Group Leadership

All five groups have two co-leads identified. Four co-leads (Rohit, Brian, Adrian, Maame) were previously approached informally. Six (Rob, Christian, Nick, Tehreem, Arwen, Molly) are new outreach.

| # | Working Group | Co-Lead 1 | Co-Lead 2 | Status |
| --- | --- | --- | --- | --- |
| 1 | AI in Clinical Practice & Operations | Rohit Sangal | Brian Patterson | Prev. discussed |
| 2 | AI Technology: Infrastructure & Data | Adrian Haimovich | Rob Turer | Mixed |
| 3 | AI Education, Training & Competency | Christian Rose | Nicholas Genes | New outreach |
| 4 | Human-AI Interaction & the Self | Maame Yiadom | Tehreem Rehman | Mixed |
| 5 | Ethical, Legal & Societal Implications | Arwen Declan | Molly Jeffery | New outreach |

Backup candidates if any co-lead declines:

- Group 3 (Education): Michael Gottlieb (Rush/ABEM), Brock Daniels (Weill Cornell)

- Group 5 (Ethics): Jared Anderson (Brown), Don Wright (Yale)

- Groups 1-2: Draw from original proposal list (Steven Horng, Scott Levin, David Beiser, Rob Turer)

# 3. Planning Committee

| Name | Role | Primary Responsibilities |
| --- | --- | --- |
| Andrew Taylor | Conference Chair | Strategy, co-lead recruitment, speaker recruitment, overall oversight |
| Moira Smith | Planning Committee | WG support, evidence briefs, Delphi survey design |
| Andrew Muck | Planning Committee | WG support, evidence briefs, conference day facilitation |
| Thomas Hartka | Planning Committee | WG support, evidence briefs, conference day facilitation |
| Matt Trowbridge | Planning Committee | WG support, evidence briefs, conference day facilitation |
| Hope Duncan | Administrative Support | Logistics, SAEM coordination, room booking, catering, budget tracking |

# 4. Revised Master Timeline

The table below is the complete task list organized by phase. This is designed to translate directly into Asana.

Critical path: Co-lead confirmations (Apr 4) → Member recruitment (Apr 18) → Kickoff meetings (Apr 19-20) → Delphi Round 1 (Apr 25-May 2) → Meeting 2 (May 2-3) → Delphi Round 2 (May 3-9) → Meeting 3 + summaries (May 10-12) → Conference day (May 21)

| Phase | Task | Owner | Deadline | Status |
| --- | --- | --- | --- | --- |
| NOW | Send co-lead invitation emails (10 emails) | Andrew | Apr 1-2 | URGENT |
| NOW | Update leader guide dates (shift timeline to Apr 1 start) | Planning Cte | Apr 2 | URGENT |
| NOW | Update WG descriptions doc (add co-lead names) | Planning Cte | Apr 2 | URGENT |
| NOW | Get confirmations from all 10 co-leads | Andrew | Apr 4 | URGENT |
| NOW | Book conference room at Atlanta Marriott Marquis | Hope/SAEM | Apr 4 | URGENT |
| Recruit | Co-leads recruit 8-10 WG members each | Co-leads | Apr 18 | NOT STARTED |
| Recruit | Planning Cte available to help source members | Planning Cte | Apr 5-18 | NOT STARTED |
| Recruit | Finalize conference agenda (1 room, 5 groups) | Andrew | Apr 11 | NOT STARTED |
| Recruit | Identify keynote speaker | Andrew | Apr 11 | NOT STARTED |
| Recruit | Identify panelists (2-3) | Andrew | Apr 11 | NOT STARTED |
| Recruit | SAEM marketing push (website, newsletter, listserv) | Hope/SAEM | Apr 7 | NOT STARTED |
| Recruit | Draft budget and get SAEM approval | Andrew/Hope | Apr 11 | NOT STARTED |
| Recruit | Set up conference registration | SAEM | Apr 11 | NOT STARTED |
| Recruit | Create AI evidence briefs for each WG | Planning Cte | Apr 18 | NOT STARTED |
| Kickoff | WG Kickoff meetings (Meeting 1) | Co-leads | Apr 19-20 | NOT STARTED |
| Kickoff | Async question drafting (each WG drafts 8-12 questions) | WG members | Apr 20-25 | NOT STARTED |
| Delphi R1 | Build Delphi Round 1 surveys (Qualtrics/Google Forms) | Planning Cte | Apr 25 | NOT STARTED |
| Delphi R1 | Distribute and collect Round 1 responses | Co-leads | Apr 25 - May 2 | NOT STARTED |
| Revise | WG Meeting 2: Review Round 1 results, revise questions | Co-leads | May 2-3 | NOT STARTED |
| Delphi R2 | Build and distribute Round 2 surveys | Planning Cte | May 3-9 | NOT STARTED |
| Delphi R2 | Collect Round 2 responses | WG members | May 5-9 | NOT STARTED |
| Final Prep | WG Meeting 3: Finalize consensus, assign presenters | Co-leads | May 10-11 | NOT STARTED |
| Final Prep | 2-page summaries due from each WG | Co-leads | May 12 | NOT STARTED |
| Final Prep | Planning Cte reviews and compiles summaries | Planning Cte | May 13-14 | NOT STARTED |
| Final Prep | Distribute compiled materials to all WG members | Planning Cte | May 15 | NOT STARTED |
| Final Prep | Finalize speaker logistics, AV, room setup | Hope/SAEM | May 15 | NOT STARTED |
| Final Prep | Create conference day slide deck/program | Planning Cte | May 16 | NOT STARTED |
| Final Prep | Dry run with co-leads (30 min Zoom) | Andrew | May 16 | NOT STARTED |
| SAEM | SAEM Annual Meeting begins |  | May 17 |  |
| SAEM | Informal co-lead check-ins at SAEM | Andrew | May 17-20 |  |
| Conf Day | CONSENSUS CONFERENCE DAY | All | May 21 |  |
| Conf Day | Present findings to SAEM Board | Andrew | May 21 PM |  |
| Post | Assign manuscript writing teams per WG | Co-leads | May 28 | NOT STARTED |
| Post | Draft manuscripts (AEM + AEM E&T) | WG teams | Jul 31 | NOT STARTED |
| Post | Submit conference proceedings to AEM | Andrew | Aug 31 | NOT STARTED |

# 5. Proposed Conference Day Agenda

Redesigned for a single room with ~150 attendees and five working groups. All sessions are in the same space, with table clusters for each WG during breakout sessions.

| Time | Session | Format |
| --- | --- | --- |
| 8:00-8:30 | Breakfast and Networking | Open |
| 8:30-8:45 | Welcome, Conference Goals, and Ground Rules | Plenary |
| 8:45-9:15 | Keynote: The Future of AI in Emergency Medicine | Plenary |
| 9:15-9:45 | Panel: From Data to Deployment (cross-cutting themes) | Panel + Q&A |
| 9:45-10:00 | Break |  |
| 10:00-11:15 | Session 1: The Research Incubator - WGs review pre-conference Delphi results, refine and prioritize research questions | 5 WGs (1 room) |
| 11:15-11:30 | Break + Room Reset |  |
| 11:30-12:15 | Session 2: Cross-Pollination - Paired WGs exchange perspectives. Tech (1+2), Training (3+4), Society (4+5) | 3 combined groups |
| 12:15-1:15 | Lunch + AI Gallery Walk (industry demos, posters) | Networking |
| 1:15-2:15 | Session 3: The Consensus - WGs reconvene to finalize research priorities, live polling for full-room consensus | 5 WGs + plenary |
| 2:15-2:30 | Break |  |
| 2:30-3:30 | Session 4: Report-Outs - Each WG presents 10-min summary of consensus priorities to full room | Plenary (50 min) |
| 3:30-4:00 | Synthesis: 10-Year Research Agenda and Next Steps | Plenary |
| 4:00-4:15 | Conference Evaluation and Closing Remarks | Plenary |
| 4:15-5:00 | Post-Conference Networking and SAEM Board Debrief | Open |

Key design decisions:

- One room throughout — WGs work at table clusters during Sessions 1, 2, and 3; the room converts to plenary for everything else

- Three WG sessions (Incubator, Cross-Pollination, Consensus) mirror the original proposal structure

- Cross-Pollination pairings: Technology (Groups 1+2), Training (Groups 3+4), Society (Groups 4+5). Group 4 appears twice because Human-AI Interaction bridges both training and societal themes.

- Gallery Walk at lunch replaces a formal industry panel; lower cost, higher engagement

- Live polling (Slido/Mentimeter) during Session 3 enables full-room consensus beyond just WG members

- Conference recording provides backup for qualitative analysis if consensus is incomplete

# 6. Estimated Budget

Working estimate for $20-30K constraint. No grant funding. Revenue from registration fees (~$150/person x 100-150 attendees = $15,000-22,500) can offset a significant portion.

| Item | Estimated Cost | Notes |
| --- | --- | --- |
| Conference room (1 room, full day) | $3,000-5,000 | Via SAEM block |
| AV equipment and tech support | $2,000-3,000 | Included w/ room? |
| Breakfast and lunch catering (~150 ppl) | $6,000-8,000 | $40-55/person |
| Coffee breaks (AM + PM) | $1,500-2,000 |  |
| Keynote speaker honorarium + travel | $2,000-3,000 | If external |
| Panelist honoraria (2-3) | $1,000-2,000 | May waive if SAEM |
| Qualtrics/survey platform | $0-500 | UVA license? |
| Printing (programs, handouts, signage) | $500-1,000 |  |
| Live polling software (Slido/Mentimeter) | $200-500 |  |
| Conference recording/transcription | $500-1,000 | For post-conf analysis |
| Miscellaneous/contingency | $2,000 |  |
| TOTAL ESTIMATED RANGE | $19,200 - $28,000 | Within $20-30K budget |

# 7. Modified Delphi Process (Compressed)

Two rounds instead of the standard three, with an 80% inclusion threshold.

## Round 1 (Apr 25 - May 2)

- Each WG drafts 8-12 candidate research questions during the kickoff meeting and async period

- Questions are formatted into a Likert-scale survey (1-9 importance rating)

- Planning committee builds and distributes surveys

- WG members have 7 days to respond

- Questions scoring ≥7 by ≥80% of respondents are included; ≤3 by ≥80% are excluded; middle items advance to Round 2

## Round 2 (May 3 - May 9)

- Meeting 2 reviews Round 1 results, revises borderline questions, and may add new ones

- Round 2 survey distributed within 24 hours of Meeting 2

- 5-day response window

- Final included questions form each WG’s consensus research priorities

## AI-Assisted Evidence Briefs

The planning committee will generate an evidence brief for each WG using AI-assisted literature synthesis, reviewed by a librarian. Each brief will provide a structured overview of the current state of research in that domain, key gaps, and recent publications. WGs validate, annotate, and build on these rather than conducting their own literature search from scratch.

# 8. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Co-leads decline invitation | MEDIUM | Delays recruitment by 1+ week | Have backup candidates ready; offer WG member role instead |
| WGs can’t recruit 8-10 members in 2 weeks | HIGH | Smaller groups, thinner consensus | Planning Cte sources candidates; accept 5-6 minimum |
| Delphi rounds get low response rates | MEDIUM | Can’t reach 80% threshold | Shorten surveys; personal follow-up; lower threshold to 70% |
| Timeline slips and summaries aren’t ready by May 15 | MEDIUM | Disorganized conference day | Planning Cte drafts summaries from raw data if needed |
| Low conference day attendance | LOW | Less diverse consensus | SAEM marketing; direct outreach; leverage Annual Meeting proximity |
| Keynote/panelists unavailable | MEDIUM | Weaker program draw | Recruit from co-lead pool or planning committee as backup |

# 9. Communication Plan

## Internal (Planning Committee)

- Weekly 30-min Zoom check-ins starting Apr 7 (Mondays)

- Shared Google Drive folder for all documents

- Asana board for task tracking (to be set up from this plan)

## Co-Lead Communication

- Initial invitation emails: April 1-2

- Welcome email with onboarding materials upon confirmation

- Bi-weekly check-in emails from Andrew (Apr 14, Apr 28, May 12)

- Ad-hoc support from planning committee members assigned 1:1 to each WG

## External / Marketing

- SAEM website listing and newsletter feature (coordinate with SAEM by Apr 7)

- Email blast to SAEM Informatics, Data Science, and AI Interest Group

- Social media posts (Twitter/X, LinkedIn) at key milestones

- Targeted outreach to EM department chairs and research directors

# 10. Deliverables and Dissemination

## Pre-Conference

- 5 AI-assisted evidence briefs (one per WG)

- 2 rounds of Delphi survey results per WG

- 5 two-page WG summaries compiling consensus research priorities

## Conference Day

- 5 ten-minute WG presentations to full room

- Live polling results capturing full-room consensus

- Conference recording and transcript

## Post-Conference

- 10-year research agenda manuscript (target: Academic Emergency Medicine, 10,000 words)

- Educational gaps manuscript (target: AEM Education and Training)

- Summary report to SAEM Board of Directors

- Timeline: manuscripts drafted by July 31, submitted by August 31

# 11. Immediate Next Steps (This Week)

These are the actions that need to happen in the next 72 hours to keep this on track:

- Send all 10 co-lead invitation emails (today, April 1)

- Update the leader guide with revised dates reflecting April 1 start (shift all dates forward by ~2 weeks)

- Email Hope Duncan to confirm room booking status at Atlanta Marriott Marquis and begin SAEM coordination

- Schedule first planning committee Zoom for the week of April 7

- Follow up with any co-leads who haven’t responded by April 3 (phone call, not just email)

- Set up shared Google Drive folder with all current documents

- Begin drafting evidence briefs — these can be started now without waiting for co-lead confirmations

- Create Asana project from this plan document